## Guidance Document
Corresponding Permit Section
A: Overall Planning (Guidance Document Requirements, Page _____ of Permit)
PERMIT PAGE # |  | PERMIT SECTION AND ELEMENT |  | COMMENTS/QUESTIONS | Permit Compliance Year (June 30th unless otherwise noted) | Permit Year | Overall Program Management Provided By The Lake County Watershed Protection District - Responsible Party | Responsible Implementing Party County of Lake | Responsible Implementing Party City of Clearlake | Responsible Implementing Party City of Lakeport
|  | E.6 | PROGRAM MANAGEMENT ELEMENT
| 20 | E.6.a | Legal Authority (update or create ordinance) |  | 2015 | 2 | Director | WPD & CDD | City Manager | City Manager
| 22 | E.6.b | Certification |  | 2015 | 2 | Director | WPD | City Manager | City Manager
| 22 | E.6.c | Enforcement Response Plan |  | 2016 | 3 | Director | WPD & CDD | City Engineer | City Manager
|  | E.7 | EDUCATION AND OUTREACH PROGRAM
| 25 | E.7.a | Public Outreach and Education
|  |  | Select outreach option. If regional program, develop agreements | The Essential Public Information Center (Betsy Cawn) plays a large part in the implementation of the public education and outreach BMP. | 2014 | 1 | Director | WPD | LC WPD | LC WPD
|  |  | (a) Develop and implement comprehensive education and outreach program |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (b)Conduct surveys 2x during permit term (1) |  | 2016 | 3 | Director | WPD | LC WPD | LC WPD
|  |  | (b)Conduct surveys 2x during permit term (2) |  | 2018 | 5 | Director | WPD | LC WPD | LC WPD
|  |  | (d)Disseminate education materials to target audiences and translate as appropriate |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (e)Utilize public input in developing outreach program |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (g)Provide water efficient/ stormwater friendly landscaping information |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (h)Promote reporting of illicit discharges |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (i)Provide pesticide/fertilizer application information |  |  | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (j)Provide materials to school children |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
|  |  | (k,l,m)Develop messaging to reduce discharges from organized car washes, mobile cleaning and pressure washing |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
| 27 | E.7.b. | Staff and Site Operator Training |  | 2016 | 3 | Director | WPD, CDD & DPW | Public Works Director | City Engineer
| 27 | E.7.b.1 | Illicit Discharge Detection and Elimination Training |  | 2016 | 3 | Director | WPD | Public Works Director | City Engineer
|  | E.7.b.2 | Construction Outreach and Education
| 28 |  | (a) Annual Permitee Staff Training | Starting in 2014, a QSD must oversee grading inspections and plan reviews. This will have an impact on implementation of the Construction requirements (Section E.10) | 2015 | 2 | Director | E&I | Public Works Director | City Engineer
| 29 |  | (b) Construction Site Operator Education |  | 2016 | 3 | Director | WPD, E&I, & CDD | Public Works Director | City Engineer
|  | E.7.b.3 | Pollution Prevention and Good Housekeeping Staff Training
| 29 |  | Biennial employee training |  | 2015 | 2 | Director | DPW | Public Works Director | City Engineer
|  | E.8 | PUBLIC INVOLVEMENT AND PARTICIPATION PROGRAM
| 30 |  | Develop program with input of the public and implement |  | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  |  | (a) Develop Public Involvement strategy |  | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  |  | (b) Consider Citizen Advisory Group | CLAC is the Citizen Advisory Group | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  |  | (c) Create Involvement Opportunities |  | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  |  | (d) Ensure public can access info about program |  | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  |  | (f) Engage in IRWMP or equivalent | Lake Co. is participating in IRWMP | 2015 | 2 | Director | WPD | PEOP/PIP Workgroup | PEOP/PIP Workgroup
|  | E.9 | ILLICIT DISCHARGE DETECTION AND ELIMINATION
| 31 | E.9.a | Outfall Mapping
|  |  | Create and maintain accurate outfall map including a site visit to each outfall |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | LC WPD | LC WPD
| 32 | E.9.b | Ilicit Discharge Source/Facility Inventory
|  |  | Create inventory of all industrial/commercial facilities and update annually |  | 2015 | 2 | Water Resources Engineer | EH & CDD | Planning Dept. | City Engineer
|  |  | Assess priority areas once during permit term |  | 2017 | 4 | Water Resources Engineer | WPD | WPD | WPD
| 33 | E.9.c | Field Sampling to Detect Illicit Discharges
|  |  | Sample any flowing outfalls while conducting E.9.a |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | WPD | WPD
|  |  | Annually sample priority area outfalls determined in E.9.a. |  | Summer 2015 | 3 | Water Resources Engineer | WPD | WPD | WPD
|  |  | Conduct follow up investigation within 72 hours if action levels exceeded |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | WPD | WPD
| 35 | E.9.d | Illcit Discharge Detection and Elimination Source Investigations and Corrective Actions
|  |  | Develop written procedures for investigations and corrective actions |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
|  |  | Once source of discharge is identified, require responsible party to correct within 72 hours of notification and verify with follow-up investigation |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
|  |  | Conduct follow up investigation within 72 hours if action levels exceeded |  | 2015 (Summer 2014) | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
| 36 | E.9.e | Spill Response Plan
|  |  | Develop plan |  | 2014 | 1 | Water Resources Engineer | WPD | DPW | City Engineer
|  | E.10 | CONSTRUCTION SITE STORM WATER RUNOFF CONTROL PROGRAM
| 37 | E.10.a | Construction Site Inventory
|  |  | Create inventory of all projects subject to local stormwater ordinance |  | 2014 | 1 | Water Resources Program Coordinator | WPD, E&I, & CDD | Planning Dept. | City Engineer
| 38 | E.10.b | Construction Plan Review and Approval Procedures
|  |  | Develop procedures to review and approve construction plan documents (i.e., erosion and sediment contol plans) | Must be QSD to review plans or supervise plan reviewers starting in 2014. | 2014 | 1 | Water Resources Program Coordinator | E&I | Planning Dept. | City Engineer
| 39 | E.10.c | Construction Site Inspection and Enforcement
|  |  | Inspect construction sites | Must be QSD to do inspections or supervise inspectors; includes public & private projects | 2015 | 2 | Water Resources Program Coordinator | E&I | Planning Dept. | City Engineer
|  | E.11 | POLLUTION PREVENTION/GOOD HOUSEKEEPING FOR PERMITTEE OPERATIONS PROGRAM
| 40 | E.11.a | Inventory of Permittee-Owned and Operated Facilities
|  |  | Develop and maintain inventory of all permittee owned or operated facilities that are a potential threat to water quality |  | 2015 | 2 | Water Resources Program Coordinator | DPW / Buildings and Grounds | DPW | PW Super
| 41 | E.11.b | Map of Permitte-owned or Operated Facilities
|  |  | Develop a map of inventoried facilities |  | 2015 | 2 | Water Resources Engineer | WPD | DPW | PW Super
| 41 | E.11.c | Facility Assessment
|  |  | Conduct comprehensive annual assessment and identify subset of facilities that could be considered hotspots |  | 2016 | 3 | Water Resource Program Coordinator | WPD | DPW | PW Super
|  |  | Document comprehensive assessment procedures and results |  | 2016 | 3 | Water Resource Program Coordinator | WPD | DPW | PW Super
| 42 | E.11.d | Stormwater Pollution Prevention Plans
|  |  | Develop SWPPPS for hotspots |  | 2017 | 4 | Water Resources Engineer | E&I | DPW | PW Super
| 43 | E.11.e | Inspections, Visual Monitoring and Remdial Action
|  |  | Quarterly visual inspection of hotspots |  | 2018 | 5 | Water Resources Program Coordinator | DPW / Buildings and Grounds | DPW | PW Super
|  |  | Annual comprehensive hotspot inspection |  | 2018 | 5 | Water Resource Program Coordinator | DPW / Buildings and Grounds | DPW | PW Super
|  |  | Quarterly hotspot visual observation of storm water and non-stormwater discharges |  | 2018 | 5 | Water Resources Program Coordinator | DPW / Buildings and Grounds | DPW | PW Super
|  |  | Non-Hotspots - Inspect each inventoried facility that is not a hotspot once during permit |  | 2018 | 5 | Water Resources Program Coordinator | DPW / Buildings and Grounds | DPW | PW Super
| 44 | E.11.f | Storm Drain System Assessment and Prioritization
|  |  | Implement procedures to assess and prioritize maintenance of storm drain system infrastructure. Assign a priority to each facility based on accumulation of sediment, trash and/or debris |  | 2015 | 2 | Water Resources Engineer | Road Super | DPW | PW Super
| 45 | E.11.g | Maintenance of Storm Drain System
|  |  | Inspect storm drain systems based on assigned priorities. Inspect high priority catch basins annually |  | 2016 | 3 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Clean high priority storm drains |  | 2016 | 3 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Label catch basins |  | 2016 | 3 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Maintain surface drainage structures |  | 2016 | 3 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Develop procedure to dispose of waste materials removed from catch basins |  | 2016 | 3 | Water Resources Engineer | Road Super | DPW | PW Super
| 45 | E.11.h | Permittee Operations and Maintenance Activities (O&M) | [5 empty] | DPW
|  |  | Develop program to assess O&M activites for potential to discharge pollutants and inspect all O&M BMPs quarterly |  | 2016 | 3 | Water Resources Engineer | DPW / Buildings and Grounds | DPW | PW Super
| 46 | E.11.i | Incorporation of Water Quality and Habitat Enhancement Features in Flood Management Facilities
|  |  | Develop and implement process for incorporating water quality and habitat enhancement into new and rehabilitated flood management projects |  | 2016 | 3 | Water Resources Engineer | WPD | DPW | PW Super
| 47 | E.11.j | Landscape Design and Maintenance
|  |  | Implement a landscape design and maintenance program to reduce the amount of water, pesticides and fertilizers used by Permittees |  | 2015 | 2 | Water Resources Engineer | Buildings and Grounds | DPW | PW Super
|  |  | Evaluate use of pesticides, herbicides and fertilizers |  | 2015 | 2 | Water Resources Engineer | Road Super / Buildings and Grounds | DPW | PW Super
|  |  | Implement best practices to reduce pesticides and fertilizers |  | 2015 | 2 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Proper dispoal of unused chemicals |  | 2015 | 2 | Water Resources Engineer | Road Super | DPW | PW Super
|  |  | Evapo-based irrigation and rain sensors |  | 2015 | 2 | Water Resources Engineer | Buildings and Grounds | DPW | PW Super
|  |  | Record amount of chemical usage |  | 2015 | 2 | Water Resources Engineer | Road Super | DPW | PW Super
|  | E.12 | POST CONSTRUCTION STORMWATER MANAGEMENT PROGRAM
| 48 | E.12.a | Post-Construction Treatment Measures
|  |  | Regulate development to comply with the following sections, E.12.b through E.12.l |  | 2015 | 2 | Director | WPD & CDD | Planning Dept. | City Engineer
| 48 | E.12.b | Site Design Measures
|  |  | Require implementation of site design measures on projects that create or replace 2,500-5,000 SF impervious area (incl single family homes) |  | 2015 | 2 | Water Resources Engineer | WPD & CDD | Planning Dept. | City Engineer
| 49 | E.12.c | Regulated Projects
|  |  | Implement standards on projects that create or replace >5,000 SF impervious area, aka Regulated Projects |  | 2015 | 2 | Water Resources Engineer | WPD & CDD | Planning Dept. | City Engineer
|  |  | Road and Utility Projects creating 5,000 sf or more that are public or fall under planning authority of a city shall comply with LID except 85th % can follow EPA Guidance on green infrastructure |  | 2015 | 2 | Water Resources Engineer | WPD & DPW | Planning Dept. | City Engineer
| 51 | E.12.d. | Source Control Measures - Regulated Projects shall implement source control measures |  | 2015 | 2 | Water Resources Engineer | WPD & CDD | Planning Dept. | City Engineer
| 52 | E.12.e | LID Standards - all Requlated Projects shall implement LID standards to treat storm water and provide baseline hydromod mgmt to meet numeric sizing criteria under E.12.e(ii)c |  | 2015 | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
| 56 | E.12.f | Hydromodification Management |  | 2016 | 3 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
| 58 | E.12.g | Enforceable Mechanisms
|  |  | Develop or modify enforceable mechanisms to implement E.12.b - E.12.f |  | 2016 | 3 | Water Resources Engineer | WPD & CDD | Planning Dept. | City Engineer
| 58 | E.12.h | Operation and Maintenance of Post-Construction Stormwater Management Measures
|  |  | Implement an O&M verification program for stormwater treatment and baseline hydromod (defined in E.12.e.ii.f) on all regulated projects |  | 2015 | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
| 60 | E.12.i | Post-Construction BMP Condition Assessment
|  |  | Inventory and assess the maintenance condition of structural post-construction BMPs within permittees jurisdiction |  | 2016 | 3 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
| 61 | E.12.j | Planning and Development Review Process
|  |  | Conduct review using an existing guide such as Municipal Regulatory Update Assistance Program |  | 2016 | 1-3 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
|  |  | Conduct an analysis of the landscape code to correct gaps hindering post construction requirements |  | 2014 | 1 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
|  |  | Complete any changes to landscape code to administer post-construction req |  | 2015 | 2 | Water Resources Engineer | WPD | Planning Dept. | City Engineer
|  | E.12.k | Post Construction Storm Water Management Requirements Based on Assessment and Maintenance of Watershed Processes |  | TBD
|  | E.12.l | Alternative Post-Construction Storm Water Management Program
|  |  | For multiple benefit projects a permittee may propose alternative Post Const. Requirements (address water quality, supply, flood control, habitat enhancement, open space preserv, recreation, climate change) |  | No date provided - permittee may propose if desired
|  | E.13 | WATER QUALITY MONITORING
|  | E.13.a. | ASBS Monitoring - MS4s that discharge to ASBS and are covered by an Ocean Plan exception comply with Attachment C |  | 2014 | 1 | N/A | N/A | N/A | N/A
| 63 | E.13.b. | TMDL Monitoring - MS4s w TMDLs must comply with Attachment G and consult with Regional Board within 1 year of effective date to determine monitoring requirements and schedule. And shall implement TMDL monitoring as specified by RB Executive Officer | Since Clearlake is subject to a TMDL, only one monitoring program is required. The LC WPD should serve as the umbrella agency overseeing TMDL implementation and associated WQ monitoring. The program must be developed in year1. | 2014 | 1 | Water Resources Program Coordinator | WPD - TBD | WPD - TBD | WPD - TBD
| 64 | E.13.c. | 303(d) Monitoring - MS4s discharging to 303(d) listed waterbodies shall consult with Regional Board within 1 year of effective date to determine whether monitoring is necessary. |  | 2014 | 1 | Water Resources Program Coordinator | WPD - TBD | WPD - TBD | WPD - TBD
|  | E.13.d. | Receiving Water Monitoring and Special Studies (Select either Receiving Water Monitoring or Special Studies, if not already conducting E.13.a, b or c monitoring) |  |  | 1
|  | E.13.d.1 | Receiving Water Monitoring |  | 2014 | 1
|  |  | Select one urban/rural site and one urban area site to monitor |  | 2014 | 1
|  |  | Monitor urban/rural and urban area sites |  | 2015 | 2
|  |  | Complete and have available a report that includes a summary of baseline data collections and discussion of monitoring program results |  | 2015 | 2
|  |  | Complete and have available a report that includes a comparison of data collection to baseline data and discussion of monitoring program results |  | 2018 | 5
|  | E.13.d.2 | Special Studies
|  |  | Develop and implement special study monitoring program and submit to Regional Board for review and approval |  | 2014 | 1
|  |  | Implement approved special study plan |  | 2015 | 2
|  |  | Complete and have available a report that includes a summary of baseline data collections and discussion of monitoring program results |  | 2015 | 2
|  |  | Complete and have available a report that includes a comparison of data collection to baseline data and discussion of monitoring program results |  | 2018 | 5
|  | E.14 | PROGRAM EFFECTIVENESS ASSESSMENT
| 70 | E.14.a | Program Effectiveness Assesment and Improvement Plan (PEAIP)
|  |  | Submit PEAIP |  | 2015 | 2 | Director | WPD | LC WPD | LC WPD
| 72 | E.14.b | Storm Water Program Modifications
|  |  | Identify and summarize BMP and/or program modifications identified in priority program areas that will be made in the next permit term |  | 2018 | 5 | Director | WPD | LC WPD | LC WPD
|  | E.15 | TOTAL MAXIMUM DAILY LOADS COMPLIANCE REQUIREMENTS
| 73 | E.15.a | Comply with all approved TMDLs (Attachment G) | The TMDL lists multiple stakeholders, some who are not part of the Clean Water Advisory Council or subject to the MS4 Permit. The LC WPD should serve as the umbrella agency for TMDL implementation of all these agencies. LC WPD will report progress annual via the MS4 report. | 2014 | 1 | Director | WPD | LC WPD | LC WPD
| 73 | E.15.b | Waste load allocations are incorporated herein by reference as enforceable parts of this Order |  | 2014 | 1 | Director | WPD | LC WPD | LC WPD
| 73 | E.15.c | Regional Board reviews TMDLs within one year of effective date and may propose modifications to requirements |  | 2014 | 1 | Director | WPD | LC WPD | LC WPD
| 74 | E.15.d | Report status of implementation via SMARTS |  | 2014 | 1 | Director | WPD | LC WPD | LC WPD
| 74 | E.15.e | Comply with Clean Water Act Sections 303d,306b and 314 |  | 2014 | 1 | Director | WPD | LC WPD | LC WPD
|  | E.16 | ANNUAL REPORTING PROGRAM
| 74 | E.16.a | Use SMARTS to report and certify | The LC Clean Water Program will continue to submit one annual report covering all jurisdictions, with each jurisdiction providing data to the WPD throughout the year. | 2014-2018 | all years | Water Resources Program Coordinator | WPD | City Engineer | City Engineer
| 74 | E.16.b | Complete and retain annual reports and make available to RWQCB during working hours |  | 2014-2018 | all years | Water Resources Program Coordinator | WPD | City Engineer | City Engineer
| 74 | E.16.c | Submit detailed written or oral report to RWQCB if directed. |  | 2014-2018 | all years | Water Resources Program Coordinator | WPD | City Engineer | City Engineer
| 75 | E.16.d | May coordinate reporting if regional programs |  | 2014-2018 | all years | Water Resources Program Coordinator | WPD | City Engineer | City Engineer